Training Needs Analysis (TNA) Report

Project: Guest Services (GS) New Hire Certification

Program Date: October 26, 2023

Prepared For: XYZ (Global Learning & Development)

1. Executive Summary

This report outlines the design strategy for the new Guest Services (GS) training curriculum. The analysis balances the client's request for a compressed timeline against the operational risks of deploying "green" crew members. We recommend a Competency-Based Approach that prioritizes safety, financial liability, and system proficiency over general knowledge.

2. Project Constraints & Requirements

- Target Audience: International new hires (IGSA); diverse backgrounds; English as a second language (ESL).

- Venue: Shoreside facility (No access to live ship systems/Front Desk).

- Technology: "Mobile-First" philosophy (Tablets/Laptops).

- Timeline: Client requested 5 Days total (including 1 Day PBOS).

- Critical Constraint: Trainees must be "Operationally Ready" to handle an assigned float and live guest interactions immediately upon boarding.

3. Data Collection & Gap Analysis

Methodology: Reviewed Job Description (March 2024), Facilitator Guides, and Operational Data (ZADM Manifests).

- Gap 1: Evaluation Misalignment (Critical)

  - Finding: The existing evaluation form weighted Soft Skills at ~80% and lacked objective measurement of Hard Skills.

  - Risk: Trainees could graduate with high scores for "friendliness" while remaining incompetent in Cash Handling and Safety protocols.

  - Solution: Implementation of a new Operations Readiness Assessment (outlined in Section 5) that introduces "Pass/Fail" gates for Safety and Cash.

- Gap 2: The "Cognitive Overload" Risk

  - Finding: The curriculum attempts to teach fleet history, deep menu knowledge, and complex Excel macros in 4 days.

  - Risk: Analysis of the ZADM V826 manifests confirms the role is data-intensive. Overloading trainees with "nice-to-know" trivia reduces retention of "must-know" compliance tasks.

  - Solution: Filter content into "Must Memorize" (Safety/Systems) vs. "Must Reference" (Menus/Ports).

4. Scheduling Recommendations

We present two options to accommodate the consecutive PBOS + Skills Training requirement.

Option A: The "Accelerated" Track (5 Days Total)

- Schedule: Day 1 (PBOS) + Days 2-5 (Skills).

- Pros: Meets client's strict timeline; lower venue/accommodation costs.

- Cons: Reduces Role-Play Simulations by 50%. High risk of deploying crew who understand theory but fail in execution.

- Prerequisite: Trainees must complete 8 hours of self-paced pre-work before arrival.

Option B: The "Proficiency" Track (Recommended - 6 Days Total)

- Schedule: Day 1 (PBOS) + Days 2-6 (Skills).

- Pros: Includes a dedicated Simulation Day (Pressure Testing).

- Justification: The cost of one extra training day is lower than the cost of one significant onboard error (e.g., a mishandled 911 call or a $500 float discrepancy).

- Cons: Higher upfront cost.

5. Assessment Strategy (New Framework)

To ensure operational readiness, the evaluation form has been redesigned with the following weighting:

- Section A: The "Red Lines" (Pass/Fail):

  - Safety: 911/Medical protocols.

  - Finance: Assigned Float Liability/Cash Balancing.

  - Integrity: GDPR/Privacy compliance.

  - Result: Failure here = Termination of training.

- Section B: Technical Proficiency (40%):

  - Timed drills on Fidelio (Check-in <3 mins).

  - Excel proficiency (VLOOKUP for manifests).

  - AIMS reporting accuracy.

- Section C: Behavioral Skills (40%):

  - Verbal Reasoning & Active Listening.

  - De-escalation of "Angry Guest" scenarios.

  - Upselling (Club Orange/Shore Excursions).

- Section D: Resourcefulness (20%):

  - Testing the ability to find information (using the Information Hub or Navigator App) rather than memorizing volatile data like menu prices.

6. Conclusion

We recommend proceeding with Option B (6 Days) and utilizing the Revised Evaluation Form. This ensures that we deploy GSAs who are not just "certified," but are safe, billable, and resilient assets to the shipboard operation.